## Change Log
Environmental Management Skills Taxonomy — Project Change Log
Schema version: 1.1 ¦ Created: March 2026 ¦ Maintained alongside taxonomy_task_sequence_v7.md ¦ Authoritative database: skills_taxonomy_workforce_v1_updated.xlsx
Entry ID | Date | Entry Type | Version / Task | Description | Competency Scope | Field(s) Affected | Before Value | After Value | Rationale / Source Document | Open Issues Created | Open Issues Resolved | Logged By
CL-001 | 2025-12-02 | Source Document Creation | Pre-Task / V1 Source | Source taxonomy text `20251202_SkillsTaxonomy_Core_V2__1_.txt` established as authoritative competency enumeration. Represents Core V2; implies a prior V1 draft that is unrecoverable. | All 215 competencies | Source text (read-only) | No structured taxonomy | 215 competencies across 6 domains, 43 skill areas | 20251202_SkillsTaxonomy_Core_V2__1_.txt (filename date) | V1/V2 source and task sequence content unrecoverable | — | JR
CL-002 | Pre-Feb 2026 | Framework Development | Tasks 1–8 | Profession family definitions (15 families F1–F15), workflow stage definitions (S1–S6), craft assignment criteria (FC/DC/SC), and ethical lens framework (L1–L5, E/I/A) produced as standing reference documents. Database initialized in Excel. | All 215 competencies (framework only; no tags populated) | profession_family_definitions.md; workflow_stage_definitions.md; craft_assignment_criteria.md; ethical_lens_framework.md | No analytical frameworks | 4 framework documents; database initialized | Framework definition documents (all four); task sequence V3 | Working records for Tasks 1–8 not preserved as standalone documents | — | JR
CL-003 | Feb 2026 | Analytical Dimension Population | Task 9 | All 215 competencies tagged with Core and Supporting profession family assignments. Governing principle: classify from competency content, not role occupancy. No boundary criteria modified during execution. | All 215 competencies | Profession family tag columns (Core / Supporting) | Untagged | All 215 tagged | taxonomy_task9_working_record.md; taxonomy_task9_completion_summary.md | F5/F7/F8 architecture confirmed as structural spine. Foundational Professional Preparation stratum identified (7 near-universal competencies). Zero-Core administrative zone documented in D3. Delphi flag list compiled. | — | JR
CL-004 | Feb 2026 | Analytical Dimension Population | Task 10 | All 215 competencies tagged with Primary and Secondary workflow stage assignments. Reform sensitivity flags applied using 6-code controlled vocabulary. 5 dual-Primary exceptions granted with explicit justification. | All 215 competencies | Workflow stage columns (Primary / Secondary); Reform sensitivity flags | Untagged | All 215 tagged; 89 competencies carry ≥1 reform flag (115 total) | taxonomy_task10_working_record.md; workflow_stage_definitions.md | — | Task 10 completion summary produced (later confirmed redundant; flagged for removal at Task 16.5) | JR
CL-005 | Feb 2026 | Analytical Dimension Population | Task 11 | All 215 competencies assigned Primary craft (FC/DC/SC) with optional Secondary. Irreducibility test applied consistently. FC/DC structural property identified: H calls predicted to cluster in FC and SC Primary contexts only. | All 215 competencies | Craft assignment columns (Primary / Secondary) | Untagged | All 215 tagged | taxonomy_task11_working_record.md; craft_assignment_criteria.md | Domain craft rationale txt files produced (6 files). Later confirmed redundant (March 2026); flagged for removal at Task 16.5 after prediction note extraction. | — | JR
CL-006 | Feb 2026 | Instrument Development | Task 12 | 5-dimension AI/robotics exposure classification instrument developed and ratified. Ac (Compressive Augmentation) category created during D6 stress test. Domain 4 pilot classification complete (105 tasks). Instrument definition embedded in domain4_task12_working_record.md Section 1.2 as canonical reference. | Domain 4 (105 tasks); instrument applicable to all 645 tasks | Automation Type; Tacit Knowledge Density; Career Ladder Position; Automation Vector; Time Horizon | No instrument; no exposure classifications | Instrument ratified; D4 classified; 4 remaining domains pending | domain4_task12_working_record.md (Section 1.2) | CRITICAL GAP CREATED: D6 was stress-test domain; Ac category created after D6 was classified. D6 Ac retrospective reclassification required for SA 6.3 and 6.8. Estimated 10–20 tasks. Becomes Pre-Task 15A. | — | JR
CL-007 | Feb 2026 | Analytical Dimension Population | Task 13 | Full exposure classification applied across 6 domains, 43 skill areas, 215 competencies at 645 tasks. Standing rules R1–R12 formalized. FC/DC structural property confirmed without exception. 9 confirmed Substitution calls (all in D6 documentation tasks). 9-task arithmetic residual documented (636 confirmed vs. 645 expected). | All 215 competencies / 645 tasks | Automation Type; Tacit Knowledge Density; Career Ladder Position; Automation Vector; Time Horizon | Unclassified (except D4 from Task 12) | Full 5-dimension classification: A=368 (57%), H=136 (21%), Ac=92 (14%), V=31 (5%), S=9 (1%) | task13_crossdomain_synthesis.md; domain exposure classification files | 3 cross-cutting gap areas forwarded to Task 14: Indigenous Data Sovereignty; Human-AI Teaming/AI Oversight; Regulatory Professional Integrity. D6 Ac retrospective gap confirmed. 9-task arithmetic residual flagged for Task 15/16 reconciliation. | CL-006 gap (D6 Ac) elevated to Pre-Task 15A requirement | JR
CL-008 | Feb 2026 | Taxonomy Structural Expansion | Task 14 | Domain 7 (Cross-Cutting Professional Practice) created as integration layer. 7 new competencies added across 2 new skill areas: SA 7.1 Professional Ethics Architecture (4 competencies) and SA 7.2 Human-AI Professional Practice (3 competencies). All D7 competencies Human-Essential. Standing Rule R10 established for D7.1 ethical lenses (E/A only). | 7 new competencies (7.1.1–7.1.4; 7.2.1–7.2.3) | Competency count; domain count; skill area count; task count | 215 competencies / 6 domains / 43 skill areas | 222 competencies / 7 domains / 45 skill areas | domain7_task14_tagging_record.txt; task14_crossdomain_synthesis.xlsx | D7.2 ethical lens values session-confirmed but NOT entered in database (L3=I, L5=I for 7.2.1 and 7.2.3; L5=I for 7.2.2). Flagged as first entries for Task 15. GitBook renders D7 as 'Cross-Cutting Professional Practice' without numeric label. | — | JR
CL-009 | Mar 2026 | Process Governance | Task Sequence V5 → V6 | Task sequence updated from V5 to V6. 4 new tasks inserted (Pre-15A, Pre-15B, 15.5, 16.5). Tasks 15 and 16 scope expanded. Session protocols and completion checks formalized for all tasks Pre-15A through Task 22. Document tier review completed. | All 222 competencies (governance change; no tag values revised) | taxonomy_task_sequence_v6.md (document governance) | taxonomy_task_sequence_v5.md (removed) | taxonomy_task_sequence_v6.md (current) | taxonomy_task_sequence_v6.md header; March 2026 tier review session | — | V5 removed from project knowledge. V3 confirmed absent. D6 exposure source document confirmed missing — remediation required at Task 16.5. Domain craft txt files confirmed redundant (remove at Task 16.5 after prediction note extraction). taxonomy_task9_completion_summary.md promoted to Tier 1 essential. | JR
CL-010 | Mar 2026 | Data Integrity Gap Identified | Pre-Task 15A (PENDING) | D6 Ac retrospective reclassification formally designated as prerequisite task. Estimated 10–20 tasks in SA 6.3 and 6.8 should reclassify from A to Ac. Must complete before Task 15 and Task 16. | Domain 6 SA 6.3 and 6.8 (~10–20 tasks) | Automation Type column for affected tasks | A (Augmentation) for affected tasks | Ac (Compressive Augmentation) after reclassification | task13_crossdomain_synthesis.md Section 8.3; domain4_task12_working_record.md Section 1.2 (Ac criterion) | Pre-Task 15A blocking Task 15 and Task 16 | — | JR
CL-011 | Mar 2026 | Data Integrity Gap Identified | Pre-Task 15B (PENDING) | D3 task description verification designated as prerequisite for Delphi instrument finalization. ~76% of Domain 3 task descriptions are source-inferred. Exposure classifications may require revision if source framing differs materially. | Domain 3 (~35 competencies / ~80 tasks) | Task description text; potentially Automation Type if descriptions revised | Source-inferred descriptions (~76% of D3) | Verified against 20251202_SkillsTaxonomy_Core_V2__1_.txt | task13_crossdomain_synthesis.md Section 8.4; taxonomy_task_sequence_v6.md | Pre-Task 15B blocking Delphi instrument finalization | — | JR
CL-012 | Mar 2026 | Known Gap (Unresolved) | Task 16.5 (PENDING) | D6 exposure source document confirmed absent from project knowledge. The domain-level working record for D6 exposure classification (analogous to domain1_task13_exposure_classification.md) was not preserved. D6 classifications were applied in session but source rationale is unrecoverable without reconstruction. Remediation plan required at Task 16.5. | Domain 6 (all 120 tasks) | D6 exposure classification provenance | Source rationale document present (in-session only; not preserved) | Absent from project knowledge | taxonomy_task_sequence_v6.md document map gap flag | D6 Delphi items may lack source rationale for reviewer dossier | — | JR
CL-013 | Mar 2026 | Process Governance | Task Sequence V6 → V7 | Task sequence updated from V6 to V7. 3 new tasks inserted (WFIC-1, WFIC-2, WFIC-3) between gap rectification and Task 15 to conduct Wildfire Intelligence Center competency analysis and potential taxonomy integration. WFIC-2 and WFIC-3 are conditional on WFIC-1 decision gate. Downstream scope notes added for Tasks 15, 15.5, 16, 16.5, 17, 20, 22. "Fire intelligence" added as third fire sub-domain value alongside "Suppression" and "Prescribed fire" in fire_context_note specification. | All 222 competencies (governance change; no tag values revised). Potential expansion to 222+n if WFIC build proceeds. | taxonomy_task_sequence_v7.md (document governance); profession_family_definitions.md (F16 pending) | taxonomy_task_sequence_v6.md | taxonomy_task_sequence_v7.md (current) | taxonomy_task_sequence_v7.md; EO 14308 (June 2025); USWFS establishment (Jan 2026) | WFIC-1 decision gate will determine whether WFIC-2/3 proceed. If yes: new profession family F16 (Wildland Fire Intelligence & Decision Support) to be defined; competency count changes; all downstream percentage/distribution findings require recalculation. | V6 superseded by V7 (remove from project knowledge after V7 confirmed operational). | JR
CL-014 | Mar 2026 | Project Knowledge Management | Pre-Task 16.5 Inventory | Project knowledge inventory conducted (pre-Task 16.5 preliminary). 63 files cataloged. 23 files identified for removal across 4 priority tiers: exact duplicates (2 pairs), administrative/fellowship documents (6 files), superseded early-stage analytical files (8 files), and completed deliverable duplicates (5 files). 3 documentation gaps identified. 2 corrections needed. New documents added: Skills_Taxonomy_Architecture_and_Methodology_for_an_Environmental_Management_Skills_Taxonomy.md (foundational research); Wildland_Fire_Workforce_Skills_and_Near-Term_Technology_Disruptions.md added to document map. | Project knowledge scope (no competency data modified) | Project knowledge file inventory | 63 files including duplicates and superseded materials | ~40 files after cleanup (pending user removal action) | project_knowledge_inventory_pre16.5.md; taxonomy_task_sequence_v7.md document map | Project instructions still reference 215/6/43 count (stale; should be 222/7/45). opm_taxonomy_crossdomain_analysis.xlsx and JRC140967_01.pdf require content review before retention decision. | Wildland_Fire_Workforce_Skills_and_Near-Term_Technology_Disruptions.md confirmed as WFIC reference source. Skills_Taxonomy_Architecture_and_Methodology document added as foundational research for Delphi defense and publication methodology. | JR

## Legend & Schema
Field | Controlled Vocabulary / Format | Notes
Entry ID | CL-NNN (sequential) | Unique identifier for each change log entry
Date | YYYY-MM-DD or descriptive (e.g., "Pre-Feb 2026") | Date of change or best estimate if exact date unrecoverable
Entry Type | Source Document Creation ¦ Framework Development ¦ Analytical Dimension Population ¦ Instrument Development ¦ Taxonomy Structural Expansion ¦ Process Governance ¦ Data Integrity Gap Identified ¦ Known Gap (Unresolved) ¦ Project Knowledge Management | Controlled vocabulary for categorizing change types
Version / Task | Task number or version transition identifier | Links entry to task sequence; "PENDING" suffix indicates work not yet executed
Description | Free text | Narrative description of what changed and why
Competency Scope | Free text with competency codes or counts | Which competencies were affected by this change
Field(s) Affected | Column names or document names | Which database fields or documents were modified
Before Value | Free text | State before the change
After Value | Free text | State after the change
Rationale / Source Document | Document filenames or references | What justified the change; traceable to project knowledge
Open Issues Created | Free text or "—" | New issues, gaps, or dependencies introduced by this change
Open Issues Resolved | Free text or "—" | Previously logged issues that this change resolves
Logged By | Initials | Person who logged the entry
HIGHLIGHTING CONVENTION
Green fill | New entries added in current version | CL-013, CL-014 are new in v1.1
Yellow fill | Entries documenting pending/unresolved work | Used sparingly for high-visibility items
SCHEMA VERSION HISTORY
v1.0 | March 2026 | Initial change log created alongside taxonomy_task_sequence_v6.md. Entries CL-001 through CL-012.
v1.1 | March 2026 | Updated alongside taxonomy_task_sequence_v7.md. Added CL-013 (V6→V7 transition, WFIC tasks) and CL-014 (project knowledge inventory). Header reference updated from v6 to v7.